Essential Considerations for

Safely Operating Cattlecon21-
The Cattle Industry Convention
 & NCBA Trade Show

August 10-12, 2021

Description of Event

2021 marks the 124th Cattle Industry Convention & NCBA Trade show. The show will be held at the Gaylord Opryland Resort & Convention Center as well as an offsite event at the Grand Ole Opry House. The event will be held August 10-12, 2021.   This event is the largest, national event for the cattle industry and attracts 8,000-9,000 cattlemen each year.

Cattle Industry Convention held jointly with:

- National Cattlemen’s Beef Association (NCBA)

- Cattlemen's Beef Promotion & Research Board (CBB)

- American National CattleWomen, Inc. (ANCW)

- CattleFax

- National Cattlemen's Foundation (NCF)

The purpose of the event is to set policy for the beef cattle industry, provide educational and informational sessions to cattle producers, Trade Show, Social events and networking among our members.

Typical Attendee:

- Average age is 45-55 years old

- 65% male 35% female

- Members come from all over the U.S. (Majority fly 75%, 25% drive)

- Businessmen and women, ranch owners and operators (not rowdy cowboys)

- Very value conscious, paid out of own pocket to attend, very polite

Past attendee position on attendance of 2021 Event (survey conducted April 2021):

- 71% of attendees of little to no concern with attending face-to-face events

- 75% have no travel restrictions

- 86% feel comfortable flying during the pandemic

- 76% plan to attend

- Top reason for NOT planning on attending in person is school/work conflicts due to date change

Overview of COVID Event Plan

This event outline has been written by NCBA in conjunction with –

Gaylord Opryland Hotel

Grand Ole Opry

Visit Music City

Freeman

JSAV

Encore Creative

Additional service providers

NCBA has created this plan with all of our service providers/vendors in mind. Most service providers have their own COVID protocol. See below/attached.

The COVID landscape is ever changing. We plan to adhere to local guidelines in place at the time of our event and will make adjustments to our overall COVID plan as needed. NCBA is committed to regularly reviewing guidelines published by the CDC, the World Health Organization, any guidelines published by Davidson Country and the City of Nashville as well as those for the Marriott Corporation/Gaylord and Ryman Hospitality for the Grand Ole Opry. NCBA understands the current laws of the country, state/province and city in which our event is being held and will continue to work with local officials to ensure the event is in compliance.

NCBA is committed to keeping our attendees, exhibitors, staff, speakers and supplier safe during this event.

Freeman Health and Safety plan-

https://go.freeman.com/health-safety

Gaylord Commitment to clean-

https://gaylordhotelsclean.marriott.com/

General Principles for Health and Safety Operations

The implementation of reasonable and practical health and safety measures is the best way to protect the environment surrounding our event. We will encourage all attendees to be mindful of these basic principles and practice them in their daily routines. With this in mind below is a list of ways that NCBA will be encouraging and reminding attendees to use these practical measures as well as some event specific plans for larger events planned.

General

Registration –

Mailing credentials prior to the event to avoid long lines in registration

Multiple registration/Check-in locations throughout meeting space

Social distancing signage

All floor markings will be of 6 foot distance and stanchions will be installed to provide the direction of the lines, one way in and a separate way out

Masks available for attendees

Small hand sanitizer as a giveaway in addition to hand sanitizer stations

Touch free payments

No cash accepted

Additional staff to keep attendees from gathering in these areas

All registration station will have plexiglass between worker and attendee

Attendees not pre-registered will be encouraged register through their mobile phones

Staff will be masked

All counters will be set socially distanced

Meetings-

Meeting room sets socially distanced as required by the Gaylord Opryland

Walk-in slide reminders (socially distance, mask reminders etc)

Hand sanitizer throughout meeting space

AV company to clean equipment between use

No shared handheld/lavalier mics

Pre-packaged individual food and beverage

Signage throughout meeting space

All rooms will be sanitized at least 2 times per day or per Gaylord Opryland recommendations and in between sessions

Staff working will be masked

Trade Show-

Designated one-way entrances and a one-way exits (see attached floor plan)

Specific locations on show floor for F&B consumption

Hand sanitizer stations throughout meeting space

High traffic areas continuous cleaning

Chuckwagon café located outside

One-way aisles- Arrows will be on floor marking direction for movement. (see attached floor plan)

Security at each entrance monitoring numbers of attendees in each hall (one out one in as needed)

Signage throughout

Deep cleaning for high traffic areas

Disinfectant fogging of trade show floor nightly

Exhibitors offered deep cleaning options for individual booths

Limited food and beverage (F&B) offered in conjunction with the trade show. F&B will be served in designated areas-mostly outside of the building.  Security will monitor numbers of attendees in each area. Attendees will be required to consume F&B in these designated areas and will not be permitted to wonder the show floor with F&B

Additional open space on the trade show floor to allow attendees in the exhibit halls and opportunity to spread out

NCBA has increased the exhibit space and expanded the trade show outside to the paved area outside the events center and has also placed some exhibits inside the events center

Staff working will be masked

Exhibitors educated on all distance standards and cleaning standards

Exhibitor personnel will be asked to be reduced

Events

Cattlemen’s College-

1000-1400 attendees

Opening reception to be held outside

Meal functions located in chuck wagon café (outside)

Refreshment breaks will be located outside

Signage throughout

Reminder announcements from moderators for each session

Breakout room sets socially distanced as required by the Gaylord Opryland

Walk-in slide reminders (socially distance, mask reminders etc)

Hand sanitizer throughout meeting space

AV company to clean equipment between use

No shared handheld/lavlier mics

Pre-packaged individual food and beverage

Signage throughout meeting space

All rooms will be sanitized at least 2 times per day or per Gaylord Opryland recommendations and in between sessions

General sessions-

2500-3500 attendees

Socially distanced seating

Slides/video during walk-in

Hand Sanitizer Stations throughout

Masks Required for attendees

Staff working will be masked

Room will be cleaned by Gaylord Opryland between sessions

Cattle Feeders Hall of Fame Awards Dinner-

300-450 attendees

Socially distanced seating

Plated Meal with limited alcohol

Pre-event reception held outside with social distanced seating

Masks required

Hand Sanitizer Stations throughout

Food buffet stations will all be staffed. No self serve

Wednesday night event-Backyard BBQ-

2500 attendees

This reception will be located outside on the events center lawn and on the Delta Portico

Event will be set socially distance per guidelines for the Gaylord Opryland hotel

F&B in Designated areas

Masks Required

Hand Sanitizer Stations throughout

Food buffet stations will all be staffed. No self serve

Pre-packaged individual F&B where possible

Staff working will be masked

Grand Ole Opry main event-

3500-4000 attendees

Socially distanced seating

Pre and post receptions located outside in plaza area

Event will be set socially distance per guidelines for the Grand Ole Opry

F&B in Designated areas

Masks Required

Hand Sanitizer Stations throughout

Social distance signage and floor stickers throughout

Food buffet stations will all be staffed. No self serve

Pre-packaged individual F&B where possible

Staff working will be masked

Grand Ole Opry -Cashville post event reception

1000-1500 attendees

Socially distanced seating

Event will be set socially distanced per guidelines for the Grand Ole Opry House

F&B in Designated areas

Masks Required

Hand Sanitizer Stations throughout

Social distance signage and floor stickers throughout

Food buffet stations will all be staffed. No self serve

Pre-packaged individual F&B where possible

Staff working will be masked

Additional receptions-

Various sizes from 25-300 attendees

No more than restricted amount for inside events

Most events placed outside

Socially distanced seating

Event will be set socially distanced per guidelines for the Gaylord Opryland hotel

F&B in Designated areas

Masks Required

Hand Sanitizer Stations throughout

Food buffet stations will all be staffed. No self serve

Pre-packaged individual F&B where possible

Staff working will be masked

Additional considerations

Sani-crew-

NCBA has hired a group call Sani-crew to be a part of all of our larger events. This group will be visible throughout the event. The Sani-crew will-

Roam trade show passing out hand sanitizer

Cleaning high traffic areas

Roam major events

Remind attendees to socially distance

Remind attendees to wear masks

Sanitation Stations-

In additional to multiple hand sanitizer stations provided by Marriott, NCBA will place hand sanitizer stations throughout the exhibit halls. NCBA will also place five “Keeping you Safe” stations around the meeting and trade show spaces that includes-

Touchless hand sanitizer stations

COVID safety video playing on a loop on a monitor

Signage reminding attendees to socially distance and wear masks.

Chatbot-

NCBA uses a chatbot service called 42 chat. This allows us to send daily reminders to attendees about best practices for keeping safe ie washing hands, wearing masks, socially distancing. Additionally, the bot allows for -

Temperature screening tracking for attendees reported to show management

Daily health questionnaires

Daily reminders to attendees to complete questionnaire

Additional Considerations cont.-

Attendee communications-

NCBA will communicate with attendees and exhibitors in the months leading up to the convention as well as onsite.

Ad in Beef Resource Guide-onsite printed program

Slides for meetings/General sessions & meeting rooms

Information placed in marketing materials and all attendee communications leading up to the event

COVID information page on event website

Know Before You Go email communication to exhibitors and attendees

Notifications via mobile app

Event regulations and COVID information located on mobile app

Event regulations and COVID information published in weekly newsletter and social media posts for attendees

COVID information section on mobile app

Exhibitor communication/education-

NCBA will hold monthly webinars leading up to the event to update exhibitors on current regulations in the area. Additionally, NCBA will be providing a series of training sessions for attendees on exhibiting in a COVID era. NCBA, in conjunction with Freeman will work with exhibitors on additional cleaning needed for individual booth spaces.

Contact tracing-

NCBA uses Eventbit by Experient. This system is on every name badge (with attendee opt-in) and readers are placed throughout the event space. This system allows us to track attendees in real time and help with any contract tracing.

Transportation-

Transportation for this event will be minimal. We will use full-size motor coaches for overflow hotels. Busses will be at reduced capacity as required by the city and county. Event transportation for the Grand Ole Opry will all be open air when possible.

Workers and any vendors working the event will be-

Required to wear masks or face coverings at all times when in the event space

Encouraged to frequently wash hands

Reminded to socially distance

Other personal protective equipment (PPE) such as gloves, face shields, etc., may be optional or required based on a risk assessment.

Symptomatic Individuals-

If an individual displays symptom of acute respiratory illness upon arrival to the venue, or becomes sick during the day and the show organizer is aware, NCBA will notify the hotel/venue as required and direct the individual to a designated location in the meeting space.

Vaccinations-

NCBA recently conducted a survey of past attendees (April 2021)-

67% of attendees have been or plan to be vaccinated prior to the convention

Current Regulations Nashville and Davidson County (as of 4/12/2021)-

Face coverings are required

Outdoor mask mandates lifted as of 4/9/2021

Events limited to 2000 (Events outside of current regulations must apply for a variance)

35sq ft per person required

Regulations are reviewed weekly and updated frequently. Adjustments to regulations are made based on the vaccination rate in Davidson county*

Exhibiting COVID requirements and expectations-

No more than three people per 10x10 space will be permitted in a booth. This includes both attendees and exhibiting personnel

All F&B in booths must be individually packaged

Booth personnel as well as any vendors contracted to work on or in you booth space must wear masks

Handshakes, hugs and other close contact greetings are discouraged

All interactive displays and high touch areas must be cleaned in between uses

Exhibiting companies are encouraged to do nightly deep cleaning of booth space

Exhibiting companies are encouraged to limit handouts

Exhibiting companies are encouraged to provide individually wrapped giveaways

Exhibiting personnel as well as attendees will be encouraged to social distance

Exhibiting companies are encouraged to evaluate booth layout to encourage social distancing

*NCBA is in constant contact with officials from the city of Nashville as well as Executive Management of the Gaylord Opryland Hotel on the regulations. NCBA’s website is regularly updated with current regulations as well as our COVID plan.